VeriVote Kenya

8-Week Development Roadmap

(Modified: Web-First Approach)

January 26 – March 22, 2026

# Executive Summary

This roadmap outlines an 8-week development plan for VeriVote Kenya — a sovereign hybrid electronic voting system built for Kenya. The system is designed for full national independence: all AI inference, encryption, and data processing run on-premise with zero dependency on foreign APIs or cloud platforms. Week 6 delivers a locally-deployed AI fraud detection layer (Isolation Forest + Llama 3.2 via Ollama) that operates fully air-gapped, directly addressing NIRU judging criteria A2 (National Self-Reliance) and Final Stage Criterion 2 (National Sovereignty).

Key Modifications from Original Plan • Web application built first with reusable REST API endpoints for future mobile app • Simplified verification: Digital receipt instead of QR code mobile scanning • Centralized vote printing system for physical backup and audit trail • All other features (blockchain, AI, encryption, distress PIN) maintained

Development Strategy • Build incrementally: Each week produces working, testable code • API-first design: All features exposed via REST endpoints • Prioritize demonstrability: Focus on features that showcase the concept • Use simulations: Where full implementation is complex, use mock data • Leave buffer: Week 8 dedicated to integration, testing, and demo preparation

## MVP Feature Scope

| IN SCOPE (MVP) | SIMPLIFIED | SIMULATED | FUTURE |
| --- | --- | --- | --- |
| Basic SBT system | Homomorphic encryption (basic) | AI fraud detection (demo data) | Full Hyperledger |
| Voter registration | ZKP (simplified) | Mixnet (visualization) | Production ZKP |
| Vote casting UI | Distress PIN | Multi-node consensus | Mobile app |
| Digital receipt | Public portal |  | Advanced AI |
| Web verification |  |  |  |
| Vote printing |  |  |  |
| Basic blockchain |  |  |  |

# Weekly Milestones

## Week 1: Foundation & Infrastructure Setup (Jan 26 – Feb 1, 2026)

Goal: Set up development environment and core infrastructure

### Day 1-2: Project Setup (Jan 26-27)

Initialize monorepo structure (backend, frontend, smart-contracts)

Set up Git repository with branching strategy

Configure TypeScript + Node.js backend with Express

Set up PostgreSQL database with initial schema

Configure Redis for caching

Set up Docker containers for local development

Create basic CI/CD pipeline (GitHub Actions)

### Day 3-4: Database Schema & Core Models (Jan 28-29)

Design and implement Voter table (id, national_id, sbt_address, created_at)

Design and implement Vote table (encrypted_vote_hash, timestamp, serial_number)

Design and implement PollingStation table

Design and implement PrintQueue table for centralized printing

Create database migrations

Write seed data for testing (100 test voters, 10 polling stations)

Create TypeORM/Prisma models and repositories

### Day 5-7: Basic Blockchain Setup (Jan 30 – Feb 1)

Set up local Ethereum testnet (Hardhat/Ganache) OR Polygon Mumbai testnet

Write basic Soul-Bound Token (SBT) smart contract in Solidity

Implement mint() function (non-transferable tokens)

Write Vote Recording smart contract (store vote hashes)

Deploy contracts to testnet

Create backend service to interact with contracts (ethers.js/web3.js)

Write unit tests for smart contracts

Week 1 Deliverables • Working development environment • Database with core tables and seed data • Deployed SBT and Vote Recording smart contracts on testnet • Basic API endpoints for voter registration

## Week 2: Voter Registration & Authentication (Feb 2-8, 2026)

Goal: Complete voter registration system with SBT minting

### Day 8-10: Voter Registration Backend (Feb 2-4)

Create API endpoint: POST /api/voters/register

Implement national ID validation (mock biometric check)

Generate Ethereum wallet for new voter

Mint SBT token and assign to voter's wallet

Store voter record in PostgreSQL with SBT address

Implement PIN generation (normal + distress PIN)

Hash PINs using Argon2 (via libsodium/Node.js crypto)

Create API endpoint: POST /api/voters/verify-pin

### Day 11-12: Authentication Flow (Feb 5-6)

Implement JWT-based session management

Create middleware for authentication checks

Implement rate limiting (prevent brute force attacks)

Add voter status tracking (registered, voted, used_distress_pin)

Write API endpoint: GET /api/voters/:id/status

### Day 13-14: Admin Dashboard (Basic) (Feb 7-8)

Create React admin portal (Next.js)

Build voter registration form

Display registered voters list with SBT addresses

Show blockchain confirmation for SBT minting

Add basic statistics dashboard (total voters, SBTs minted)

Week 2 Deliverables • Complete voter registration API • SBT minting working end-to-end • PIN authentication (normal + distress) • Basic admin dashboard showing registered voters

## Week 3: Vote Casting & Cryptographic Core (Feb 9-15, 2026)

Goal: Build vote casting interface with encryption and receipt generation

### Day 15-17: Web-Based Voting Interface (Feb 9-11)

Create React voting interface (Next.js web application)

Build PIN entry screen

Create candidate selection UI (presidential race + sample down-ballot)

Implement vote review screen

Add multi-language support (English/Swahili)

Create accessible UI (large buttons, high contrast)

Design responsive layout for various screen sizes

### Day 18-19: Basic Encryption & Hashing (Feb 12-13)

Install Microsoft SEAL (or use simpler library for MVP)

Implement basic homomorphic encryption OR use AES-256 + plan upgrade path

Create vote serialization format (JSON → encrypted → hash)

Generate SHA-256 hash of encrypted vote

Create API endpoint: POST /api/votes/cast

### Day 20-21: Receipt Generation & Blockchain Recording (Feb 14-15)

Generate unique serial number for each vote

Create digital receipt with: serial number, timestamp, blockchain tx hash

Build receipt display page showing vote confirmation

Create API endpoint: GET /api/receipts/:serial

Write blockchain transaction to record vote hash

Update smart contract to emit VoteCast event

Store encrypted vote in PostgreSQL as backup

Update voter status to 'voted'

Week 3 Deliverables • Functional web-based voting interface • Vote encryption working • Digital receipt generation with serial number • Votes recorded on blockchain • End-to-end vote casting flow working

## Week 4: Web Verification Portal & Print System (Feb 16-22, 2026)

Goal: Build web-based verification and centralized vote printing for backup

### Day 22-24: Web Verification System (Feb 16-18)

Create web-based receipt verification page

Build serial number lookup interface

Implement cryptographic verification (server-side)

Verify vote hash matches encrypted payload

Query blockchain API to confirm vote is recorded

Create API endpoint: GET /api/votes/verify/:serial

Display verification result page (checkmark/error)

Show vote details (timestamp, blockchain confirmation)

Add printable receipt option for voters

### Day 25-26: Centralized Vote Printing System (Feb 19-20)

Design print queue database schema

Create API endpoint: POST /api/print-queue/add

Build print job processing service

Implement secure print format (vote hash, serial, timestamp)

Create admin interface for print queue management

Build batch printing functionality

Add print status tracking (queued, printing, completed)

Implement print verification/reconciliation

### Day 27-28: API Documentation & Mobile-Ready Endpoints (Feb 21-22)

Document all REST API endpoints with Swagger/OpenAPI

Ensure all endpoints return consistent JSON responses

Add CORS configuration for future mobile app

Create API authentication tokens for mobile clients

Build API rate limiting per client

Test all endpoints for mobile compatibility

Create API versioning strategy (v1)

Week 4 Deliverables • Working web-based verification portal • Receipt verification with blockchain query • Centralized vote printing system operational • Print queue management interface • Fully documented REST API ready for mobile consumption

## Week 5: Public Portal & Transparency Features (Feb 23 – Mar 1, 2026)

Goal: Build public verification portal and blockchain explorer

### Day 29-31: Public Verification Portal (Feb 23-25)

Create Next.js portal with responsive design

Build homepage with real-time election statistics

Create vote lookup page (by serial number)

Display blockchain confirmation and timestamp

Build blockchain explorer page

Show recent blocks with vote counts

Add turnout statistics (by region, polling station)

### Day 32-33: Real-Time Dashboard (Feb 26-27)

Set up WebSocket connection for real-time updates

Create live vote counter

Build polling station status map (Google Maps or simple)

Add charts for turnout trends (Chart.js/Recharts)

Display system health indicators (blockchain, API status)

Add print queue statistics to dashboard

### Day 34-35: Distress PIN Handler & Multiple Voting (Feb 28 – Mar 1)

Implement distress PIN detection in backend

Create silent flagging system (no visible indication)

Build notification system (SMS via Africa's Talking API)

Implement multiple voting logic (supersede previous vote)

Create admin interface to view distress PIN alerts

Add time-lock protection (unlimited votes first 12hrs, freeze last 2hrs)

Week 5 Deliverables • Public verification portal live • Blockchain explorer functional • Real-time dashboard with statistics • Distress PIN system working • Multiple voting capability implemented

## Week 6: Sovereign AI Security Layer & Tallying (Mar 2-8, 2026)

Goal: Implement locally-deployed AI fraud detection with full data sovereignty — no voter data leaves Kenyan infrastructure

### Day 36-38: Anomaly Detection & Rule Engine (Mar 2-4)

Set up Python microservice for AI models (FastAPI) — runs fully on-premise

Install scikit-learn, numpy, pandas; create Isolation Forest anomaly detector

Generate synthetic Kenyan election training data (simulate fraud patterns locally)

Train model on 5 features: voting_velocity, temporal_deviation, geographic_cluster_score, repeat_attempt_rate, distress_correlation

Create API endpoint: POST /api/ai/analyze-voting-pattern → returns anomaly_score 0–100

Build deterministic rule engine (fully auditable): 3+ distress votes same station/30min → CRITICAL; velocity > 3× average → HIGH

Implement alerting: score > 70 triggers alert pipeline; all decisions logged with feature values for audit (D2 Transparency)

No external API calls at any stage — entire detection pipeline runs on local Kenyan infrastructure (A2 National Self-Reliance)

### Day 39-40: Sovereign LLM Integration for Explainability (Mar 5-6)

Deploy Ollama locally on hackathon GPU (T4) — open-source LLM runtime, zero data egress

Pull Llama 3.2 8B (4-bit quantised, fits in ~5GB VRAM) — no foreign API dependency at runtime

Write prompt templates: feed anomaly_score + feature values + rule triggers → Llama → plain-English alert for IEBC officers

Generate contextual risk assessment: 'Station X shows 3× normal velocity with 2 distress flags since 14:00 — recommend immediate verification'

Build AI security dashboard in admin portal: flagged patterns list, anomaly score trend chart, per-station risk level, LLM alert feed

All LLM inference logs stored locally — supervisors can reconstruct every explanation (Stage 2 D2 Auditability)

Sovereignty note: system operates fully air-gapped; no OpenAI / foreign API keys required in production (Final Stage Criterion 2)

### Day 41-42: Decryption Ceremony & Election Results (Mar 7-8)

Implement ElGamal decryption ceremony: IEBC admin triggers tally — encrypted votes decrypted in batch using private key held by system

NOTE: ElGamal as implemented is multiplicatively homomorphic (not additively); decryption ceremony approach is correct for this stack — SEAL/Paillier upgrade path documented for future

Simulate threshold key custody: display ceremony log showing each vote decrypted and counted (auditability demonstration)

Build results display page: candidate vote counts, turnout percentage, station-by-station breakdown

Add cryptographic proof of tally: SHA-256 hash of full results JSON published on-chain as tamper-evident seal

Create downloadable audit report (PDF): tally summary, distress flag count, anomaly alerts fired, AI scores, blockchain TX references

Include print queue reconciliation: compare printed ballot count vs digital tally — flag discrepancies

Sovereignty checkpoint: confirm full election cycle completed with zero foreign API dependencies

Week 6 Deliverables • AI fraud detection system operational • Real-time anomaly scoring • OpenAI-powered alert generation • AI security dashboard • Basic tallying system with results display

## Week 7: Polish, Security, and Simulations (Mar 9-15, 2026)

Goal: Add missing features, build simulations, and harden security

### Day 43-44: Mixnet Simulation (Mar 9-10)

Create visual mixnet demonstration

Build animated UI showing vote shuffling through nodes

Implement simulated Chaumian mixing (visualization only)

Show ZKP verification at each shuffle stage

Add this to public portal as education tool

### Day 45-46: Security Hardening (Mar 11-12)

Conduct security audit of all API endpoints

Implement rate limiting on all public endpoints

Add input validation and sanitization

Set up HTTPS/TLS for all connections

Configure CORS policies

Add helmet.js security headers

Implement logging and monitoring (Winston/Datadog)

Set up error tracking (Sentry)

Secure print queue endpoints

### Day 47-49: Demo Data & Scenarios (Mar 13-15)

Create comprehensive demo dataset (1000 voters, 100 polling stations)

Generate realistic voting patterns

Simulate fraud scenarios (for AI detection demo)

Create coercion scenario (distress PIN usage)

Build demo script for live presentation

Record video walkthrough of key features

Prepare printed vote samples for demo

Week 7 Deliverables • Mixnet visualization complete • Security hardening complete • Comprehensive demo dataset • Fraud simulation scenarios • Demo script ready

## Week 8: Integration, Testing & Final Presentation (Mar 16-19, 2026)

Goal: Complete end-to-end testing, fix bugs, and prepare final demo

### Day 50-52: End-to-End Testing (Mar 16)

Run complete election simulation (50+ voters)

Test all user journeys (voter, admin, observer)

Verify blockchain integrity

Test web interface on multiple browsers/devices

Load testing (simulate 1000+ concurrent voters)

Fix critical bugs

Test distress PIN flow end-to-end

Verify AI alerts trigger correctly

Test print queue under load

Verify receipt verification flow

### Day 53-54: Documentation (Mar 17)

Write comprehensive README.md

Create API documentation (Swagger/OpenAPI)

Document deployment process

Write technical architecture document

Create user guide (PDF)

Record demo videos for each feature

Document mobile API integration guide for future development

### Day 55-56: Final Presentation Prep (Mar 19)

Create pitch deck (PowerPoint/Google Slides)

Rehearse live demo

Prepare backup demo (in case live fails)

Deploy to cloud (AWS/Heroku/Vercel)

Set up public demo site

Test demo on presentation hardware

Prepare Q&A responses

Final polish on UI/UX

Week 8 Deliverables • Fully tested, bug-free system • Complete documentation • Live demo site deployed • Presentation materials ready • Project ready for demo

# Technical Implementation Details

## Core Technology Stack

| Category | Technologies |
| --- | --- |
| Backend | Node.js v20+, TypeScript v5+, Express.js, PostgreSQL v16+, Redis v7+ |
| Frontend | React v18+, Next.js v14+, Tailwind CSS v3.4+, Chart.js v4+ |
| Blockchain | Hardhat, Polygon Mumbai Testnet, Solidity v0.8.20+, ethers.js, OpenZeppelin |
| Cryptography | Microsoft SEAL (optional), libsodium, Node.js crypto, snarkjs (simplified) |
| AI/ML | Python v3.11+, FastAPI, scikit-learn v1.4+, OpenAI API (GPT-4o-mini) |
| Printing | Node-printer, PDF generation (pdfkit), Print queue service |
| DevOps | Docker, GitHub Actions, AWS/Heroku/Vercel, PM2, Winston, Sentry |

Backend API:       Node.js 20 + TypeScript + Express.js + Prisma ORM

Database:          PostgreSQL 16 (primary) + Redis 7 (OTP cache / rate limiting)

Blockchain:        Hardhat local EVM testnet (Polygon RPC for production); ethers.js; Solidity SBT contract

Encryption:        ElGamal 2048-bit FFDHE RFC 7919 (vote encryption); Argon2id (PIN hashing); SHA-256 (vote hash)

Identity / KYC:    Persona (ID document + liveness, inline iframe); WebAuthn / FIDO2 (fingerprint at polling station)

Frontend:          Next.js 15 + React + Tailwind CSS + Recharts + Socket.IO client

Real-Time:         Socket.IO (WebSocket + polling fallback) — live vote counter, distress alerts

Notifications:     Africa's Talking (SMS, Kenyan provider); Nodemailer SMTP (email)

AI — Detection:    Python FastAPI + scikit-learn Isolation Forest + deterministic rule engine (fully local)

AI — Explanation:  Ollama + Llama 3.2 8B (locally deployed, 4-bit quantised, GPU T4) — ZERO foreign API dependency

Sovereignty:       All runtime services run on Kenyan infrastructure; no voter data transmitted abroad

## Repository Structure

verivote-kenya/

├── backend/                    # Node.js + TypeScript API
│   └── src/
│       ├── controllers/        # API route handlers
│       ├── models/             # Database models
│       ├── services/           # Business logic
│       ├── blockchain/         # Smart contract interactions
│       └── print-service/      # Centralized printing
├── frontend/                   # Next.js web portal (voting + public)
│   └── pages/
│       ├── vote/               # Voting interface
│       ├── verify/             # Receipt verification
│       ├── admin/              # Admin dashboard
│       └── public/             # Public statistics
├── smart-contracts/            # Solidity contracts
│   └── contracts/
│       ├── SoulBoundToken.sol
│       └── VoteRecorder.sol
├── ai-service/                 # Python ML service
├── docs/                       # Documentation
└── docker-compose.yml          # Local development